## Sheet1
Task | Start date | Days to complete
Planning and data collection | 2022-03-16 | 4
Research and requirement specification | 2022-03-20 | 5
DFD Modeling | 2022-03-26 | 7
UML Diagrams | 2022-04-01 | 14
UI/UX Design | 2022-04-16 | 6
Implementation | 2022-04-22 | 8
Testing | 2022-04-30 | 5